## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US-TA-001 | TA Register System Account | As a TA, I want to register for the system, so that I can access the TA recruitment platform. | Must Have | 1 | 1. Registration is only available via QM email. 2. Email verification is required within 24 hours. 3. Password must contain uppercase, lowercase, and numbers (8+ chars). | 3 | QM Email Integration | 2026-04-01 | 2026-04-07
US-TA-002 | TA Create Personal Profile | As a TA, I want to create a personal profile/resume, so that MOs can review my qualifications. | Must Have | 1 | 1. Supports editing major, GPA, and teaching experience. 2. Allows uploading PDF resume (≤10MB). 3. Drafts are saved for 7 days. | 4 | PDF Preview Support | 2026-04-01 | 2026-04-07
US-TA-003 | TA View Positions | As a TA, I want to browse MO posted positions, so that I can find suitable roles. | Should Have | 2 | 1. Filterable by course name and vacancies. 2. Displays MO name, deadline, and responsibilities. 3. Option to bookmark favorite positions. | 3 | Sorted by Deadline | 2026-04-15 | 2026-04-22
US-TA-004 | TA Apply for Job | As a TA, I want to submit a job application, so that I can be considered for recruitment. | Should Have | 2 | 1. Requires selecting available working hours. 2. Shows "Application Successful" popup. 3. Allows viewing application status (Pending/Rejected). | 3 | 1 Application Limit | 2026-04-15 | 2026-04-22
US-TA-005 | TA Receive Interview | As a TA, I want to receive interview notifications, so that I can confirm the interview details. | Could Have | 3 | 1. Sent to QM email and in-system message. 2. Option to "Confirm" or "Request Reschedule". 3. Includes meeting link/address. | 2 | Push Notification | 2026-04-29 | 2026-05-05
US-MO-001 | MO Post Position | As a MO, I want to post a TA position, so that I can recruit teaching assistants. | Must Have | 1 | 1. Requires course name, slots, duties, deadline. 2. Option to set priority conditions (e.g., GPA ≥ 3.0). 3. Preview functionality before final submission. | 4 | Course Library Select | 2026-04-01 | 2026-04-07
US-MO-002 | MO Review Resumes | As a MO, I want to review TA applications, so that I can shortlist candidates. | Must Have | 1 | 1. Sortable by GPA and major. 2. Allows viewing/downloading PDF attachments. 3. Mark resumes as "Pass" or "Reject" (with reason). | 4 | Reason ≥ 10 chars | 2026-04-01 | 2026-04-07
US-MO-003 | MO Send Invites | As a MO, I want to send interview notifications, so that I can arrange interviews. | Should Have | 2 | 1. Batch send to multiple "Passed" TAs. 2. Customizable interview template (time/mode). 3. Track TA confirmation status. | 3 | Resend if Unconfirmed | 2026-04-15 | 2026-04-22
US-MO-004 | MO Confirm Hire | As a MO, I want to confirm hiring results, so that the recruitment cycle is complete. | Should Have | 2 | 1. Mark TAs as "Hired", "Waitlist", or "Rejected". 2. Auto-email notification to TA. 3. Export shortlist to Excel. | 3 | Excel Export | 2026-04-15 | 2026-04-22
US-MO-005 | MO View History | As a MO, I want to view past recruitment records, so that I can analyze previous results. | Could Have | 3 | 1. Filter by year/semester. 2. Displays applications, passes, and hires. 3. View detailed TA information for hires. | 2 | 2 Year Data Limit | 2026-04-29 | 2026-05-05
US-Admin-001 | Admin Manage MO Accounts | As an Admin, I want to add/delete MO accounts, so that I can manage system permissions. | Must Have | 1 | 1. Validates staff ID when adding MOs. 2. Confirmation required before deletion. 3. View account status (Active/Disabled). | 3 | Disabled MO = Paused Positions | 2026-04-01 | 2026-04-07
US-Admin-002 | Admin Import Courses | As an Admin, I want to import the school course library, so that MOs can select courses. | Must Have | 1 | 1. Bulk import via Excel (Code/Name/Credits). 2. Preview data and detect duplicates/errors. 3. Manual edit functionality for courses. | 4 | Excel Template Provided | 2026-04-01 | 2026-04-07
US-Admin-003 | Admin View Progress | As an Admin, I want to monitor recruitment progress, so that I can oversee the whole process. | Should Have | 2 | 1. Filter by MO name and course name. 2. Displays applications, screens, and hires. 3. Export progress report to Excel. | 3 | Semester Statistics | 2026-04-15 | 2026-04-22
US-Admin-004 | Admin Manage Feedback | As an Admin, I want to handle system feedback, so that the system runs smoothly. | Should Have | 2 | 1. View feedback list sorted by time. 2. Mark status (Pending/In Progress/Resolved). 3. Reply to feedback (visible to submitters). | 3 | 48hr Response Target | 2026-04-15 | 2026-04-22
US-Admin-005 | Admin Export Data | As an Admin, I want to export system usage data, so that I can generate reports. | Could Have | 3 | 1. Monthly/Quarterly export options. 2. Data includes TA signups and MO postings. 3. PDF export with charts (e.g., Pie chart). | 2 | Chart Visualization | 2026-04-29 | 2026-05-05